## Project Plan Summary
/Non Project/PSP Fundamentals & Advanced/Program 5
PSP2.1 Project Plan Summary
Project Settings
Project Owner | Fredy Benavides Gordillo
Start Date | 2017-04-03 20:13
Completion Date | 2017-04-05 10:07 |  |  |  | Completed: *
Keywords
Language | Java
Overall Metrics
Summary | Plan | Actual | To Date
Size/Hour | 49.6 | 52.6 | 43
Planned Time | 0.17292 |  | 0.77917
Actual Time |  | 0.18681 | 0.85625
CPI (Cost-Performance Index) |  |  | 0.91
% Reuse | 0% | 0% | 1.56%
% New Reusable | 0% | 0% | 0%
Test Defects/KLOC or equivalent | 1.54 | 0 | 1.13
Total Defects/KLOC or equivalent | 29.3 | 29.7 | 29.4
Yield % | 63.2% | 71.4% | 65.4%
Code Review Rate | 976 | 442 | 655
% Appraisal COQ | 7.47% | 22.7% | 10.8%
% Failure COQ | 10.8% | 8.55% | 10.3%
COQ A/F Ratio | 0.69 | 2.65 | 1.05
PQI | 0.02 | 0.81 | 0.05
Program Size
| Plan | Actual | To Date
Base (B) | 0 | 0 | 0
Deleted (D) | 0 | 0 | 0
Modified (M) | 0 | 0 | 0
Added (A) | 206 | 236 | 884
Reused (R) | 0 | 0 | 14
Added and Modified (A+M) | 206 | 236 | 884
Total Size (T) | 206 | 236 | 898
Total New Reusable | 0 | 0 | 0
Estimated Proxy Size (E) | 206 | 26 | 678
Upper Prediction Interval (70%) | N/A
Lower Prediction Interval (70%) | N/A
Time In Phase
| Plan | Actual | To Date | To Date %
Planning | 0.019444 | 0.025 | 0.10069 | 11.8%
Design | 0.018056 | 0.05 | 0.12083 | 14.1%
Design Review | 0.0041667 | 0.020139 | 0.036111 | 4.22%
Code | 0.095833 | 0.040972 | 0.41181 | 48.1%
Code Review | 0.0090278 | 0.022222 | 0.05625 | 6.57%
Compile | 0.010417 | 0.0090278 | 0.048611 | 5.68%
Test | 0.0083333 | 0.0069444 | 0.039583 | 4.62%
Postmortem | 0.0076389 | 0.0125 | 0.042361 | 4.95%
Total | 0.17292 | 0.18681 | 0.85625
Total Time UPI (70%) | N/A
Total Time LPI (70%) | N/A
Defects Injected
| Plan | Actual | To Date | To Date %
Before Development | 0 | 0 | 0 | 0%
Planning | 0 | 0 | 0 | 0%
Design | 2.54 | 3 | 11 | 42.3%
Design Review | 0 | 0 | 0 | 0%
Code | 3.49 | 4 | 15 | 57.7%
Code Review | 0 | 0 | 0 | 0%
Compile | 0 | 0 | 0 | 0%
Test | 0 | 0 | 0 | 0%
Total | 6.03 | 7 | 26
Defects Removed
| Plan | Actual | To Date | To Date %
Planning | 0 | 0 | 0 | 0%
Design | 0 | 0 | 0 | 0%
Design Review | 1.27 | 2 | 6 | 23.1%
Code | 1.59 | 0 | 5 | 19.2%
Code Review | 0.95 | 3 | 6 | 23.1%
Compile | 1.9 | 2 | 8 | 30.8%
Test | 0.32 | 0 | 1 | 3.85%
Total | 6.03 | 7 | 26
After Development | 0 | 0 | 0
Defect Removal Efficiency
| Plan | Actual | To Date
Defects/Hour - Design Review | 12.8 | 4.14 | 6.92
Defects/Hour - Code Review | 4.52 | 5.62 | 4.44
Defects/Hour - Compile | 7.77 | 9.23 | 6.86
Defects/Hour - Test | 1.57 | 0 | 1.05
DRL (DLDR/UT) | 8.17 | 3.93 | 6.58
DRL (Code Review/UT) | 2.88 | 5.34 | 4.22
DRL (Compile/UT) | 4.95 | 8.77 | 6.51
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Report generated at 10:56 AM on Apr 5, 2017